## Room Design
Room | Spritesheet Completed | Footprints Completed | Shadowsheet Completed | Added to world | Floor Collider Completed | Object Collider Completed | Doorways completed | View other rooms | Chairs/Tables/Inventory | Lighting Effects | Bugs and Iniformation
Inn Floor 1 Room 1 | Y | Y | Y | Y | Y | Y | Y
Inn Floor 1 Room 2 | Y | Y | Y | Y | Y | Y | Y
Inn Floor 2 Hall | Y | Y | Y | Y | Y | Y | Y
Inn Floor 2 Room 1 | Y | Y | Y | Y | Y | Y | Y
Inn Floor 2 Room 2 | Y | Y | Y | Y | Y | Y | Y
Inn Floor 2 Room 3 | Y | Y | Y | Y | Y | Y | Y
Inn Floor 2 Room 4 | Y | Y | Y | Y | Y | Y | Y
Inn Floor 2 Balcony | Y | Y | Y | Y | Y | Y | Y
Overworld | Y | Y | N/A | Y | N/A | N/A
Bakery Floor 2 Room 1 | Y | Y | Y | Y | Y | Y | Y |  |  |  | Ladder needs footprint
Bakery Floor 1 Room 3 | Y | Y | Y | Y | Y | Y | Y |  |  |  | Door needs footprint, split up boxes or make one collier for all
Bakery Floor 1 Room 2 | Y | Y | Y | Y | Y | Y | Y |  |  |  | Ladder missing rightmost pixel
Bakery Floor 1 Room 1 | Y | Y | Y | Y | Y | Y | Y
ManorHouse 1 Floor 2 Room 1 | Y | Y | Y | Y | Y | Y | Y |  |  |  | Seat missing rightmost pixel, Chest missing rightmost pixel
Manorhouse 1 Floor 1 Room 1 | Y | Y | Y | Y | Y | Y | Y |  |  |  | Missing rightmost pixel for most objects
ManorHouse 2 Floor 1 Room 1 | Y | Y | Y | Y | Y | Y | Y |  |  |  | Please add 1 more pixel to the container and empty pot (invisible for alignment) and stairs. Need Complete table and wall component block as a separate object, stairs needs an even number of pixels wide, Footprint missing for container
ManorHouse 2 Floor 2 Room 1 | Y | Y | Y | Y | Y | Y | Y
Shack Floor 1 Room 1 | Y | Y | Y | Y | Y | Y | Y
Vineyard Foor 1 Room 1 | Y | Y | Y | Y | Y | Y | Y |  |  |  | Need Front and Middle Door and respective collider sprites
Vineyard Foor 1 Room 2 | Y | Y | Y | Y | Y | Y | Y |  |  |  | Need collider for cellar and cellar door
Vineyard Floor 1 Room 3 | Y | Y | Y | Y | Y | Y | Y |  |  |  | Rightmost pixel for shadow missing from chairs
Vineyard Floor 2 Room 1 | Y | Y | Y | Y | Y | Y | Y |  |  |  | Need collider for cellar and cellar door (Same as above)
Customs House Floor 1 Room 1 | Y | Y | Y | Y | Y | Y | Y
Customs House Floor 2 Room 1 | Y | Y | Y | Y | Y | Y | Y
Church Floor 1 Room 1 | Y | Y | Y | Y | Y | Y | Y | Y
Church Floor 1 Room 2 | Y | Y | Y | Y | Y | Y | Y | Y
GuardHouse Floor 1 Room 1 | Y | Y | Y | Y | Y | Y | Y
GuardHouse Floor 2 Room 1 | Y | Y | Y | Y | Y | Y | Y
Blacksmith Floor 1 Room 1 | Y | Y | Y | Y | Y | Y | Y
Blacksmith Floor 1 Room 2 | Y | Y | Y | Y | Y | Y | Y
Blacksmith Floor 2 Room 1 | Y | Y | Y | Y | Y | Y | Y
ManorHouse 3 Floor 1 Room 1 | Y | Y | Y | Y | Y | Y | Y |  |  |  | Oven footprint too big
ManorHouse 3 Floor 2 Room 1 | Y | Y | Y | Y | Y | Y | Y |  |  |  | Missing spot on stairs

## Overworld Objects
Objects | Sprites Created | Shadow Added | Collision Body Created | Doors Created | Exterior Objects Created
Docks | Y | Y | Y
Bakery Exterior | Y | Y | Y
ManorHouse 1 Exterior | Y | Y | Y
ManorHouse 2 Exterior | Y | Y | Y
ManorHouse 3 Exterior | Y | Missing Frontal Sprite | Y
Shack Exterior | Y | Y | Y
Vineyard Exterior | Y | Needs sprite covering floor | Y
Customs House Exterior | Y | Y | Test Sorting
Church Exterior | Y | Y | Y |  |  | 1
Guardhouse Exterior | Y | Y | Y
Inn Exterior | Y | Shadow needs to include back portion | Y
Church Exterior | Y | Think backside part of shadow is incorrect (Fig 1) | Y
Blacksmith Exterior | Y | Y | Y

## Character Design
Character | Forward | Back | Sit | Hold Lantern | Eating Rats | Hold Baby | Hat Remove | Ground Pickup | Interact
AnneTheCarpenter | Shaded | Shaded | Shaded
BeatriceTheApprentice | Shaded | Shaded | Shaded
BertTheFarmer | Uploaded | Uploaded | Uploaded
Cloakguy 1 | Animated | Animated | Animated
Cloakguy 2 | Animated | Animated | Animated
Cloakguy 3 | Animated | Animated | Animated
Cloakguy 4 | Animated | Animated | Animated
Cloakguy 5 | Animated | Animated | Animated
EleanorTheVinekeeper | Uploaded | Uploaded | Uploaded
ElismiTheCountess | Animated | Animated | Animated
ErnestTheFarmer | Animated | Animated | Animated
GerdnessTheBaker | Uploaded | Uploaded | Uploaded
GorgeTheBlacksmith | Uploaded | Uploaded
HamenTheInnkeeper | Animated | Animated | Animated
IrvaTheBarmaiden | Uploaded | Uploaded
IvanTheButcher | Animated | Animated | Animated
JenTheDaughter | Uploaded | Uploaded | Uploaded
JohanTheLibrarian | Animated | Animated | Animated
JohnTheCoward | Animated | Animated | Animated
MackenzieThePriest | Uploaded | Uploaded |  | Uploaded
MaryTheOrphan | Animated | Animated | Animated |  | Uploaded
MinnieTheSeamstress | Uploaded | Uploaded | Uploaded
MurphyTheFishmonger | Uploaded | Uploaded | Uploaded
OwenThePardoner | Uploaded | Uploaded | Uploaded
PanaceaTheDoctor | Animated | Animated | Animated
ParrTheNobleman | Uploaded | Uploaded | Uploaded
RafaelTheMerchant | Animated | Animated | Animated
RohezTheDrunk | Uploaded | Uploaded | Uploaded
SueThePainter | Uploaded | Uploaded | Uploaded |  |  | Uploaded
WiselTheApprentice | Uploaded | Uploaded | Uploaded
Guard | Uploaded | Uploaded | Uploaded
Player | Tested | Tested | Tested |  |  |  | Uploaded | Tested | Uploaded
| Designed | Lined | Colored | Shaded | Uploaded | Animated | Tested |  | Bug
Note on A30: Jiashen Wang:Rohez Spirtehseet not the same as others

## Music Design
Music | Type | Author/Source | Duration | Description | Location in Game
A major - D7 | Ambience | Albert | 0:34 | Guitars
Misc 1 | Ambience | Kevin
Misc 2 | Ambience | Kevin | 1:22 | Harpsichord, Eeery
Misc 3 | Ambience | Kevin | 1:46 | It's Me, Mario

## Sound Effects
Sound Effects | Author/Source | Duration | Status | Location
Walking - Dirt
Walking - Grass
Walking - Wood
Walking - Stairs
Door Open 1
Door Open 2
Activate Object - Default
Mouse Click
Attack - Hand
Interact - Trade
Interact - Steal
Climb on bed
Get off bed
Drink liquid