## Room Design
Room | Spritesheet Completed | Footprints Completed | Shadowsheet Completed | Added to world | Floor Collider Completed | Object Collider Completed | Doorways completed | View other rooms | Chairs/Tables/Inventory | Lighting Effects | Bugs and Iniformation
Inn Floor 1 Room 1 | Y | Y | Y | Y | Y | Y | Y
Inn Floor 1 Room 2 | Y | Y | Y | Y | Y | Y | Y
Inn Floor 2 Hall | Y | Y | Y | Y | Y | Y | Y
Inn Floor 2 Room 1 | Y | Y | Y | Y | Y | Y | Y
Inn Floor 2 Room 2 | Y | Y | Y | Y | Y | Y | Y
Inn Floor 2 Room 3 | Y | Y | Y | Y | Y | Y | Y
Inn Floor 2 Room 4 | Y | Y | Y | Y | Y | Y | Y
Inn Floor 2 Balcony | Y | Y | Y | Y | Y | Y | Y
Overworld | Y | Y | N/A | Y | N/A | N/A
Bakery Floor 2 Room 1 | Y | Y | Y | Y | Y | Y | Y |  |  |  | Ladder needs footprint
Bakery Floor 1 Room 3 | Y | Y | Y | Y | Y | Y | Y |  |  |  | Door needs footprint, split up boxes or make one collier for all
Bakery Floor 1 Room 2 | Y | Y | Y | Y | Y | Y | Y |  |  |  | Ladder missing rightmost pixel
Bakery Floor 1 Room 1 | Y | Y | Y | Y | Y | Y | Y
ManorHouse 1 Floor 2 Room 1 | Y | Y | Y | Y | Y | Y | Y |  |  |  | Seat missing rightmost pixel, Chest missing rightmost pixel
Manorhouse 1 Floor 1 Room 1 | Y | Y | Y | Y | Y | Y | Y |  |  |  | Missing rightmost pixel for most objects
ManorHouse 2 Floor 1 Room 1 | Y | Y | Y | Y | Y | Y | Y |  |  |  | Please add 1 more pixel to the container and empty pot (invisible for alignment) and stairs. Need Complete table and wall component block as a separate object, stairs needs an even number of pixels wide, Footprint missing for container
ManorHouse 2 Floor 2 Room 1 | Y | Y | Y | Y | Y | Y | Y
Shack Floor 1 Room 1 | Y | Y | Y | Y | Y | Y | Y
Vineyard Foor 1 Room 1 | Y | Y | Y | Y | Y | Y | Y |  |  |  | Need Front and Middle Door and respective collider sprites
Vineyard Foor 1 Room 2 | Y | Y | Y | Y | Y | Y | Y |  |  |  | Need collider for cellar and cellar door
Vineyard Floor 1 Room 3 | Y | Y | Y | Y | Y | Y | Y |  |  |  | Rightmost pixel for shadow missing from chairs
Vineyard Floor 2 Room 1 | Y | Y | Y | Y | Y | Y | Y |  |  |  | Need collider for cellar and cellar door (Same as above)
Customs House Floor 1 Room 1 | Y | Y | Y | Y | Y | Y | Y
Customs House Floor 2 Room 1 | Y | Y | Y | Y | Y | Y | Y
Church Floor 1 Room 1 | Y | Y | Y | Y | Y | Y | Y | Y
Church Floor 1 Room 2 | Y | Y | Y | Y | Y | Y | Y | Y
GuardHouse Floor 1 Room 1 | Y | Y | Y | Y | Y | Y | Y
GuardHouse Floor 2 Room 1 | Y | Y | Y | Y | Y | Y | Y
Blacksmith Floor 1 Room 1 | Y | Y | Y | Y | Y | Y | Y
Blacksmith Floor 1 Room 2 | Y | Y | Y | Y | Y | Y | Y
Blacksmith Floor 2 Room 1 | Y | Y | Y | Y | Y | Y | Y
ManorHouse 3 Floor 1 Room 1 | Y | Y | Y | Y | Y | Y | Y |  |  |  | Oven footprint too big
ManorHouse 3 Floor 2 Room 1 | Y | Y | Y | Y | Y | Y | Y |  |  |  | Missing spot on stairs

## Character Design
Character | Forward | Back | Sit | Hold Lantern | Eating Rats | Hold Baby | Hat Remove | Ground Pickup | Interact
AnneTheCarpenter | Shaded | Shaded | Shaded
BeatriceTheApprentice
BertTheFarmer | Uploaded | Uploaded | Uploaded
Cloakguy 1 | Uploaded | Uploaded | Uploaded
Cloakguy 2 | Uploaded | Uploaded | Uploaded
Cloakguy 3 | Uploaded | Uploaded | Uploaded
Cloakguy 4 | Uploaded | Uploaded | Uploaded
Cloakguy 5 | Uploaded | Uploaded | Uploaded
EleanorTheVinekeeper | Shaded | Shaded | Shaded
ElismiTheCountess | Uploaded | Uploaded | Uploaded
ErnestTheFarmer | Animated | Animated | Animated
GerdnessTheBaker | Shaded | Shaded | Shaded
GorgeTheBlacksmith | Shaded | Shaded
HamenTheInnkeeper | Animated | Animated | Animated
IrvaTheBarmaiden | Shaded | Shaded
IvanTheButcher | Uploaded | Uploaded | Uploaded
JenTheDaughter
JohanTheLibrarian | Uploaded | Uploaded | Uploaded
JohnTheCoward | Uploaded | Uploaded | Uploaded
MackenzieThePriest | Shaded | Shaded |  | Shaded
MaryTheOrphan | Uploaded | Uploaded | Uploaded |  | Shaded
MinnieTheSeamstress | Shaded | Shaded | Shaded
MurphyTheFishmonger | Shaded | Shaded | Shaded
OwenThePardoner | Shaded | Shaded
PanaceaTheDoctor | Uploaded | Uploaded | Uploaded
ParrTheNobleman | Shaded | Shaded | Shaded
RafaelTheMerchant | Animated | Animated | Animated
RohezTheDrunk | Uploaded | Uploaded | Uploaded
SueThePainter | Shaded | Shaded | Shaded |  |  | Shaded
WiselTheApprentice
Guard | Designed | Designed | Designed
Player | Tested | Tested | Tested |  |  |  | Uploaded | Tested | Uploaded
| Designed | Lined | Colored | Shaded | Uploaded | Animated | Tested
Note on A30: Jiashen Wang:Rohez Spirtehseet not the same as others